## Tasks
Task_ID | Phase | Area | Task_Title | Description | Acceptance_Criteria | Estimated_Hours | Priority | Dependencies | Owner | Status
MIG-001 | Planning | Program | ADR: NestJS + Prisma + PostgreSQL | Lock stack: NestJS for HTTP/WebSocket APIs, Prisma as ORM and migration tool for PostgreSQL only, target hosting for API and DB. Document versions (Node LTS, Nest, Prisma). Out of scope: MySQL unless separate ADR. | ADR or one-pager committed; team agrees; no ambiguous ORM/DB choice. | 4 | P0 |  |  | Not_Started
MIG-002 | Planning | Security | Secrets and key management | DATABASE_URL for Prisma (server only), JWT keys, PayPal, SMTP, SMS, S3. Nest ConfigModule + env validation. Never expose DB URL to Vite. | Checklist of secrets; .env.example for API without real values; frontend only VITE_API_URL and public keys. | 4 | P0 | MIG-001 |  | Not_Started
MIG-003 | Planning | Inventory | Inventory Supabase usage in frontend | List files using supabase client: auth, from(), rpc(), functions.invoke(), storage, realtime channels. | Matrix: file path, call type, replacement Nest route or WS event. | 6 | P0 |  |  | Not_Started
MIG-004 | Planning | Inventory | Inventory Edge Functions and cron | Map each supabase/functions/* to future Nest module (controller + service); note env vars and triggers. | All functions covered; none orphaned. | 5 | P0 |  |  | Not_Started
MIG-005 | Planning | Inventory | RPCs, SQL functions, and RLS inventory | List supabase.rpc calls and SQL functions in migrations; extract RLS policies per table. Plan Prisma-level authorization (guards) replacing RLS. | RPC matrix with parameters; RLS rules summarized; has_role and other security paths mapped to Nest guards. | 10 | P1 |  |  | Not_Started
MIG-006 | Database | Infrastructure | Provision target PostgreSQL | Create production-grade Postgres (RDS, Cloud SQL, managed K8s, or self-hosted). Configure backups, TLS, extensions needed by schema (uuid, pgcrypto, etc.), connection limits. | Connection from bastion or CI works with SSL; backup window defined; DATABASE_URL format documented for Prisma. | 8 | P0 | MIG-001 |  | Not_Started
MIG-007 | Database | Schema | Deploy full SQL schema to target | Replay supabase/migrations in order on empty DB, OR pg_dump --schema-only from Supabase and restore to target. Include public app tables, types, indexes, constraints, SQL functions used by RPCs. Exclude or separately handle Supabase auth/storage extensions if not cloning auth schema. | prisma db execute or psql: no errors; \dt lists expected tables; functions exist for RPC parity plan. | 12 | P0 | MIG-006 |  | Not_Started
MIG-008 | Database | Data | Migrate ALL existing rows (bulk copy) | Full data migration: pg_dump --data-only from Supabase (or provider backup restore), OR logical replication, OR table-ordered COPY with FK checks deferred. Include every business table and large tables (orders, logs, email state). Plan maintenance window or brief read-only on source. After load: run ANALYZE; fix sequences with setval to max(id). | Per-table row count matches source (automated diff); random FK spot-checks pass; sequences produce new IDs without collision. | 18 | P0 | MIG-007 |  | Not_Started
MIG-009 | Database | Data | Post-migration data validation | Script comparing source Supabase vs target: counts, checksums on critical tables, max timestamps. Document acceptable deltas (e.g. excluded auth schema). | Signed validation report; stakeholders approve before API cutover. | 8 | P0 | MIG-008 |  | Not_Started
MIG-010 | Database | Schema | Dry run on staging clone | Repeat MIG-007–MIG-009 against staging Postgres; rehearse timing and rollback (drop schema / restore snapshot). | Staging holds full schema + representative or full copy; runbook updated with actual durations. | 12 | P0 | MIG-009 |  | Not_Started
MIG-011 | Database | Auth | User identity migration off Supabase Auth | Export or map auth.users to application user table: preserve UUIDs where stores.user_id references them OR one-time relink. Password: export bcrypt hashes if Supabase allows or force password reset. MFA factors: re-enroll in Nest flow. | All active users can authenticate via new Nest auth; FK from stores to user ids valid; documented exceptions. | 24 | P0 | MIG-008 |  | Not_Started
MIG-012 | Database | Storage | Migrate Storage files (store-profiles bucket) | Copy objects from Supabase Storage to S3-compatible bucket; preserve paths or update stores.profile_picture_url in bulk. Script with retry and verification. | Object count/size matches or URLs updated and images load from new base URL. | 10 | P0 | MIG-008 |  | Not_Started
MIG-013 | Prisma | Prisma | prisma db pull (introspect target DB) | Point DATABASE_URL at migrated Postgres; run prisma db pull to generate models from live schema. Review public schema only; ignore supabase internal schemas unless needed. | schema.prisma generated; prisma validate passes; no accidental drop of tables. | 3 | P0 | MIG-007 |  | Not_Started
MIG-014 | Prisma | Prisma | Hand-tune Prisma schema | Fix @@map/@map for snake_case, relation names, enums, Json fields, Unsupported types. Add indexes in Prisma if missing. Document views: use prisma.$queryRaw or migrate to tables. | prisma generate succeeds; Prisma Client typings usable in Nest services; team review complete. | 14 | P0 | MIG-013 |  | Not_Started
MIG-015 | Prisma | Prisma | Prisma Migrate baseline for future changes | Brownfield: baseline existing DB — prisma migrate diff or documented initial migration marking current state; from then on use prisma migrate dev/deploy for schema changes only (no drift from manual SQL without Prisma). | CI applies migrations to empty test DB OR migrate deploy is no-op on prod clone; drift detection documented. | 8 | P1 | MIG-014 |  | Not_Started
MIG-016 | Prisma | Prisma | Seed script (optional) for dev | prisma/seed.ts for local dev subset; never required for prod (prod uses real migrated data). | npm run prisma:seed creates minimal dev data for Nest local run. | 3 | P2 | MIG-014 |  | Not_Started
MIG-020 | Backend | NestJS | Bootstrap NestJS project | nest new or monorepo app; ConfigModule, ValidationPipe, global exception filter, health controller (/health), structured logging (pino), Swagger optional. | GET /health 200; lint/test pipeline green; Dockerfile optional. | 6 | P0 | MIG-001 |  | Not_Started
MIG-021 | Backend | Prisma | PrismaService and Nest integration | Official pattern: PrismaService extends PrismaClient, onModuleInit connect, onModuleDestroy disconnect; global module or per-request as needed. Unit test with test DB or docker-compose Postgres. | Any module can inject PrismaService; e2e test runs query against test DB; CI runs prisma generate. | 5 | P0 | MIG-014 |  | Not_Started
MIG-022 | Backend | Security | CORS and rate limiting | @nestjs/throttler on auth/OTP; CORS for Vite origins. | Preflight OK; brute-force OTP returns 429 in test. | 4 | P1 | MIG-020 |  | Not_Started
MIG-023 | Backend | NestJS | Feature module layout | Organize AuthModule, StoresModule, OrdersModule, etc.; each service uses PrismaService; DTOs with class-validator. | Architecture diagram or README; no circular deps. | 5 | P1 | MIG-021 |  | Not_Started
MIG-030 | Auth | Auth | Registration and password login (Prisma users) | Nest guards + JWT; bcrypt/argon2; user rows in Postgres via Prisma; map user id to stores.user_id. | E2E: register, login, JWT valid; Prisma shows user row. | 12 | P0 | MIG-011 |  | Not_Started
MIG-031 | Auth | Auth | Email OTP login and verification | Replace Supabase OTP with Nest endpoints; store OTP in customer_otp_codes or equivalent via Prisma. | Flows match Login, StoreRegistration, ForgotPassword UX contract. | 10 | P0 | MIG-030 |  | Not_Started
MIG-032 | Auth | Auth | Session refresh and logout | Refresh tokens stored in DB or Redis; Nest endpoints for refresh/logout. | Token rotation works; logout invalidates refresh. | 8 | P0 | MIG-030 |  | Not_Started
MIG-033 | Auth | Auth | Password update and reset | Secure reset tokens in DB (Prisma); update password hashes. | Reset flow E2E; tokens single-use. | 8 | P0 | MIG-031 |  | Not_Started
MIG-034 | Auth | Auth | Admin MFA (replace Supabase MFA) | TOTP/WebAuthn in Nest; Prisma for factors if stored. | AdminLogin parity; cannot bypass MFA for admin role. | 16 | P0 | MIG-030 |  | Not_Started
MIG-035 | Auth | Auth | Roles and has_role replacement | Prisma queries to user_roles; RolesGuard on admin controllers. | Non-admin JWT rejected; unit tests on guard. | 6 | P0 | MIG-030 |  | Not_Started
MIG-036 | Auth | Auth | Lovable cloud-auth integration | integrations/lovable/index.ts: pass Nest JWT/session or deprecate. | Documented behavior; no broken dev flow. | 3 | P2 | MIG-032 |  | Not_Started
MIG-040 | Domain_API | Stores | Stores CRUD and generate_store_id | Nest service with Prisma transactions; port generate_store_id logic from SQL or app layer. | Parity with supabase-store and AuthContext store creation. | 8 | P0 | MIG-021 |  | Not_Started
MIG-041 | Domain_API | Stores | check_store_duplicate endpoint | POST; Prisma query matching RPC behavior. | Same duplicate detection as current RPC tests. | 3 | P0 | MIG-040 |  | Not_Started
MIG-042 | Domain_API | Products | Global/store products and portfolio APIs | Prisma for global_products, store_products, store_portfolios, stock_entries. | Admin CRUD; FK integrity. | 12 | P0 | MIG-040 |  | Not_Started
MIG-043 | Domain_API | Orders | Customer orders and notifications | Prisma for customer_orders, store_notifications; scoped by store. | EmployeeDashboard operations covered. | 12 | P0 | MIG-040 |  | Not_Started
MIG-044 | Domain_API | Orders | Public order RPCs as REST | Implement former RPCs via Prisma/raw SQL in service: get_public_store_by_slug, slots, qr products, validate customer, order status. | StoreOrder works against Nest API only. | 14 | P0 | MIG-043 |  | Not_Started
MIG-045 | Domain_API | Settings | Store customers and time slots | Prisma CRUD for store_customers, store_time_slots. | Settings.tsx parity. | 10 | P0 | MIG-040 |  | Not_Started
MIG-046 | Domain_API | Support | Support tickets and messages | Prisma for support_tickets, support_messages. | SupportChatbot + AdminSupportPanel parity. | 8 | P1 | MIG-040 |  | Not_Started
MIG-047 | Domain_API | Community | Community chat REST | Prisma for community_channels, community_messages. | Polling OK until realtime. | 5 | P1 | MIG-040 |  | Not_Started
MIG-048 | Domain_API | Admin | Audit and billing reads | Prisma for audit_logs, coupons, store_subscriptions, webhook_logs, invoices. | Admin billing and revenue panels load. | 10 | P1 | MIG-035 |  | Not_Started
MIG-049 | Domain_API | Feedback | Feedback API | Prisma feedback table. | AppHeader feedback path works. | 3 | P2 | MIG-021 |  | Not_Started
MIG-050 | Integrations | Email | Transactional email in Nest | Services + queues; Prisma for email logs/state; port Edge templates. | Staging emails send; idempotent queue. | 18 | P0 | MIG-020 |  | Not_Started
MIG-051 | Integrations | Email | Unsubscribe and suppression | Controllers for unsubscribe/suppression; Prisma for tokens/suppressed_emails. | Unsubscribe.tsx points to Nest; secured. | 8 | P0 | MIG-050 |  | Not_Started
MIG-052 | Integrations | OTP | Customer OTP send/verify | Nest + Prisma customer_otp_codes. | Settings customer OTP flow E2E. | 8 | P0 | MIG-045 |  | Not_Started
MIG-053 | Integrations | SMS | Order SMS | Port send-order-sms; call from order status service. | Sandbox SMS or logged success. | 6 | P1 | MIG-043 |  | Not_Started
MIG-054 | Integrations | PayPal | PayPal checkout in Nest | Controller/service; Prisma for subscriptions/invoices; update PayPalCheckout + Settings URLs to Nest. | Sandbox end-to-end; webhooks to Nest. | 14 | P0 | MIG-020 |  | Not_Started
MIG-055 | Integrations | Orders | notify-store-order | Nest service calling email/SMS. | New order notifies store like today. | 5 | P0 | MIG-050 |  | Not_Started
MIG-056 | Integrations | Billing | check-subscriptions cron | @nestjs/schedule or external cron hitting secured endpoint. | Runs on schedule; logs errors. | 5 | P1 | MIG-054 |  | Not_Started
MIG-057 | Integrations | OTP | Registration OTP | If distinct from general OTP, port to Nest. | StoreRegistration completes. | 5 | P1 | MIG-031 |  | Not_Started
MIG-060 | Realtime | Realtime | WebSocket gateway (Nest) | @nestjs/websockets or socket.io; JWT on handshake; event names for orders/notifications/support/community. | Design doc + PoC broadcast. | 10 | P1 | MIG-032 |  | Not_Started
MIG-061 | Realtime | Realtime | Replace Supabase channels in frontend | Connect to Nest WS; remove supabase.channel. | <1s latency staging; reconnect OK. | 14 | P1 | MIG-060 |  | Not_Started
MIG-070 | Storage | Files | Upload API and S3 integration in Nest | Multipart or signed URL; update profile_picture_url via Prisma. Align with MIG-012 migrated objects. | New uploads work post-cutover; public URLs consistent. | 8 | P0 | MIG-020 |  | Not_Started
MIG-080 | Frontend | Client | API client (VITE_API_URL) | fetch/axios to Nest; Bearer JWT; no Supabase env in prod. | Single client module; typed errors. | 4 | P0 | MIG-020 |  | Not_Started
MIG-081 | Frontend | Client | Migrate auth pages and AuthContext | Remove supabase.auth; call Nest. | QA auth flows; no supabase in auth files. | 14 | P0 | MIG-030 |  | Not_Started
MIG-082 | Frontend | Client | Replace lib/supabase-store | api/store.ts calling Nest; Prisma-backed routes. | No supabase imports in store module. | 6 | P0 | MIG-040 |  | Not_Started
MIG-083 | Frontend | Client | Migrate Settings and EmployeeDashboard | Includes PayPal, OTP invokes, uploads to Nest. | Checklist sign-off. | 20 | P0 | MIG-045 |  | Not_Started
MIG-084 | Frontend | Client | Migrate StoreOrder and StoreRegistration | Public flows to Nest. | E2E staging. | 10 | P0 | MIG-044 |  | Not_Started
MIG-085 | Frontend | Client | Migrate admin UI components | AdminDashboard, panels, analytics, PayPal, chatbot. | No supabase in listed components. | 18 | P0 | MIG-048 |  | Not_Started
MIG-086 | Frontend | Client | Wire ResetPassword route in App.tsx | If product needs /reset-password. | Route works with Nest reset token. | 2 | P2 | MIG-033 |  | Not_Started
MIG-087 | Frontend | Client | Remove @supabase/supabase-js | Delete client wrapper; clean env. | Build passes; grep no supabase. | 3 | P1 | MIG-085 |  | Not_Started
MIG-090 | QA | Testing | API contract tests (Nest + Prisma test DB) | Jest + supertest or Pact; prisma migrate reset for CI DB. | CI green: auth, orders, admin denial. | 10 | P1 | MIG-043 |  | Not_Started
MIG-091 | QA | Testing | E2E against staging | Playwright/Cypress full journeys on Vite + Nest + migrated DB. | Nightly green on staging. | 10 | P1 | MIG-084 |  | Not_Started
MIG-092 | Cutover | Ops | Production cutover runbook | Final incremental data sync if needed (delta after MIG-008); DNS to Nest; VITE_API_URL; freeze Supabase writes; rollback plan. | Runbook approved; dry run completed. | 8 | P0 | MIG-009 |  | Not_Started
MIG-093 | Cutover | Ops | Monitoring and backups | APM on Nest; Postgres backups; Prisma query logging in prod cautiously. | Alerts; restore drill. | 6 | P0 | MIG-092 |  | Not_Started
MIG-094 | Cutover | Ops | Decommission Supabase | After stability; archive backup; revoke keys. | Zero traffic 2+ weeks; costs stopped. | 3 | P2 | MIG-093 |  | Not_Started